## Project Burndown
Sprint | Sprint Xref | End Date | Burndown | Net Changes | Velocity | Burnup | Total Points | Changes per Sprint | Projected Change | Projected Burndown | Planned Burndown
Sprint 1 | \Release v2.0\Sprint 1 | 2015-09-04 | 305 | 0 | 6 | 6 | 311
Sprint 2 | \Release v2.0\Sprint 2 | 2015-09-18 | 285.5 | -7 | 19.5 | 25.5 | 318 | 7
Sprint 3 | \Release v2.0\Sprint 3 | 2015-10-02 | 268.5 | -16 | 17 | 42.5 | 327 | 9 | -16 | 268.5 | 268.5
Sprint 4 | \Release v2.0\Sprint 4 | 2015-10-16 | [6 empty] | -24 | 250.25 | 239.5
Sprint 5 | \Release v2.0\Sprint 5 | 2015-10-30 | [6 empty] | -32 | 232 | 229
Sprint 6 | \Release v2.0\Sprint 6 | 2015-11-13 | [6 empty] | -40 | 213.75 | 209
Sprint 7 | \Release v2.0\Sprint 7 | 2015-11-27 | [6 empty] | -48 | 195.5 | 189
Sprint 8 | \Release v2.0\Sprint 8 | 2015-12-11 | [6 empty] | -56 | 177.25 | 170
Sprint 9 | \Release v2.0\Sprint 9 | 2015-12-25 | [6 empty] | -64 | 159 | 159
Sprint 10 | \Release v2.0\Sprint 10 | 2016-01-08 | [6 empty] | -72 | 140.75 | 140
Sprint 11 | \Release v2.0\Sprint 11 | 2016-01-22 | [6 empty] | -80 | 122.5 | 100
Sprint 12 | \Release v2.0\Sprint 12 | 2016-02-05 | [6 empty] | -88 | 104.25 | 100
Sprint 13 | \Release v2.0\Sprint 13 | 2016-02-19 | [6 empty] | -96 | 86 | 60
Sprint 14 | \Release v2.0\Sprint 14 | 2016-03-04 | [6 empty] | -104 | 67.75 | 60
Sprint 15 | \Release v2.0\Sprint 15 | 2016-03-18 | [6 empty] | -112 | 49.5 | 44
Sprint 16 | \Release v2.0\Sprint 16 | 2016-04-01 | [6 empty] | -120 | 31.25 | 24
Sprint 17 | \Release v2.0\Sprint 17 | 2016-04-15 | [6 empty] | -128 | 13 | 3
Sprint 18 | \Release v2.0\Sprint 18 | 2016-04-29 | [6 empty] | -136 | -5.25 | -9
Sprint 19 | \Release v2.0\Sprint 19 | 2016-05-13 | [6 empty] | -144 | -23.5 | -17
Sprint 20 | \Release v2.0\Sprint 20 | 2016-05-27 | [6 empty] | -152 | -41.75 | -17
Average Velocity |  |  | 18.25
Average Increase |  |  | 8

## Backlog
ID | Work Item Type | Story Points | Iteration Path | Title 1 | State | Tags | Created Date
2104 | User Story | 2 | \Release v2.0\Sprint 1 | User Story 1 | Closed |  | 2015-09-01 11:02
2110 | User Story | 0.5 | \Release v2.0\Sprint 1 | User Story 2 | Closed |  | 2015-09-01 13:53
1975 | User Story | 1 | \Release v2.0\Sprint 1 | User Story 3 | Closed |  | 2015-08-24 13:07
1974 | User Story | 8 | \Release v2.0\Sprint 1 | User Story 4 | Closed |  | 2015-08-24 13:07
1973 | User Story | 5 | \Release v2.0\Sprint 1 | User Story 5 | Closed |  | 2015-08-24 13:06
2178 | User Story | 1 | \Release v2.0\Sprint 2 | User Story 6 | Closed |  | 2015-09-15 12:40
1876 | User Story | 5 | \Release v2.0\Sprint 2 | User Story 7 | Closed |  | 2015-08-10 15:32
1877 | User Story | 3 | \Release v2.0\Sprint 2 | User Story 8 | Closed |  | 2015-08-10 15:45
1913 | User Story | 8 | \Release v2.0\Sprint 3 | User Story 9 | Active |  | 2015-08-14 09:15
1264 | User Story | 8 | \Release v2.0\Sprint 3 | User Story 10 | Active |  | 2015-06-02 14:17
2197 | User Story | 13 | \Release v2.0\Sprint 4 | User Story 11 | New |  | 2015-09-21 10:19
2191 | User Story | 5 | \Release v2.0\Sprint 4 | User Story 12 | New |  | 2015-09-16 14:30
2193 | User Story | 3 | \Release v2.0\Sprint 4 | User Story 13 | New |  | 2015-09-17 09:56
1916 | User Story | 3 | \Release v2.0\Sprint 4 | User Story 14 | New |  | 2015-08-14 10:23
1908 | User Story | 5 | \Release v2.0\Sprint 4 | User Story 15 | New |  | 2015-08-13 13:47
1349 | User Story | 2 | \Release v2.0\Sprint 5 | User Story 16 | New |  | 2015-06-15 14:55
1969 | User Story | 5 | \Release v2.0\Sprint 5 | User Story 17 | New |  | 2015-08-21 17:02
1918 | User Story | 3 | \Release v2.0\Sprint 5 | User Story 18 | New |  | 2015-08-14 10:28
1915 | User Story | 0.5 | \Release v2.0\Sprint 5 | User Story 19 | New |  | 2015-08-14 10:20
1925 | User Story | 20 | \Release v2.0\Sprint 6 | User Story 20 | New |  | 2015-08-14 11:30
1924 | User Story | 20 | \Release v2.0\Sprint 7 | User Story 21 | New |  | 2015-08-14 11:29
2189 | User Story | 8 | \Release v2.0\Sprint 8 | User Story 22 | New |  | 2015-09-16 10:15
1926 | User Story | 3 | \Release v2.0\Sprint 8 | User Story 23 | New |  | 2015-08-14 11:35
1814 | User Story | 8 | \Release v2.0\Sprint 8 | User Story 24 | New |  | 2015-08-03 13:55
1939 | User Story | 8 | \Release v2.0\Sprint 9 | User Story 25 | New |  | 2015-08-17 13:51
2038 | User Story | 1 | \Release v2.0\Sprint 9 | User Story 26 | New |  | 2015-08-25 08:39
1907 | User Story | 2 | \Release v2.0\Sprint 9 | User Story 27 | New |  | 2015-08-13 13:11
1993 | User Story | 13 | \Release v2.0\Sprint 10 | User Story 28 | New |  | 2015-08-24 13:44
1282 | User Story | 3 | \Release v2.0\Sprint 10 | User Story 29 | New |  | 2015-06-08 10:50
1570 | User Story | 3 | \Release v2.0\Sprint 10 | User Story 30 | New |  | 2015-07-06 13:29
1927 | User Story | 40 | \Release v2.0\Sprint 11 | User Story 31 | New |  | 2015-08-14 11:44
1914 | User Story | 40 | \Release v2.0\Sprint 13 | User Story 32 | New |  | 2015-08-14 09:28
1352 | User Story | 1 | \Release v2.0\Sprint 15 | User Story 33 | New |  | 2015-06-15 15:16
1315 | User Story | 8 | \Release v2.0\Sprint 15 | User Story 34 | New |  | 2015-06-12 09:29
1928 | User Story | 5 | \Release v2.0\Sprint 15 | User Story 35 | New |  | 2015-08-14 11:56
1909 | User Story | 2 | \Release v2.0\Sprint 15 | User Story 36 | New |  | 2015-08-13 14:00
1917 | User Story | 20 | \Release v2.0\Sprint 16 | User Story 37 | New |  | 2015-08-14 10:25
1265 | User Story | 8 | \Release v2.0\Sprint 17 | User Story 38 | New |  | 2015-06-02 14:18
1185 | User Story | 13 | \Release v2.0\Sprint 17 | User Story 39 | New |  | 2015-05-28 22:06
1186 | User Story | 8 | \Release v2.0\Sprint 18 | User Story 40 | New |  | 2015-05-28 22:10
1484 | User Story | 1 | \Release v2.0\Sprint 18 | User Story 41 | New |  | 2015-06-26 08:30
1774 | User Story | 3 | \Release v2.0\Sprint 18 | User Story 42 | New |  | 2015-07-24 14:14
1307 | User Story | 8 | \Release v2.0\Sprint 19 | User Story 43 | New |  | 2015-06-12 08:07

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | 2015-09-15 12:40 | 1
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General